# ContractIQ Cohort Delivery Plan

Motor Insurance Claims Intelligent Document Processing Platform
17 August to 17 September 2026

Purpose. Deliver a demo-ready, human-governed motor claims platform that accepts claim documents, classifies and extracts evidence, validates consistency and coverage, identifies reviewable fraud indicators, and prepares a Claims Adjuster decision package.

Planning basis. The cohort will first prove the claim workflow with controlled sample data, then connect Azure services and complete a repeatable end-to-end demonstration. The Claims Adjuster remains responsible for every approval, rejection, and request for more information.

# Delivery Outcome

| Area | Cohort outcome by 17 September |
| --- | --- |
| Workflow | LangGraph orchestration runs validation, extraction, fraud, coverage, assessment, settlement recommendation, and a single Claims Adjuster review stage. |
| Data | Raw files stored in Azure Blob Storage; claim, document, review-task, and audit metadata persisted in PostgreSQL. |
| AI | Azure Document Intelligence supports OCR; Azure OpenAI provides controlled visual and semantic reasoning with deterministic safeguards. |
| Demo | Frontend submits a claim package, shows processing status, presents review evidence, and records a human decision. |

# Plan at a Glance

| Period | Milestone | Exit evidence |
| --- | --- | --- |
| 17 to 23 Aug | Foundation and Agent 1 | Upload, validation, classification, completeness checks, test samples |
| 24 to 30 Aug | Agent 2 and triage | Extraction, field checks, cross-document consistency, workflow routing |
| 31 Aug to 6 Sep | Risk and coverage agents | Fraud indicators, coverage rules, policy retrieval, reviewer evidence |
| 7 to 13 Sep | Integration and hardening | Azure services, PostgreSQL audit trail, UI integration, end-to-end test |
| 14 to 17 Sep | Closeout and demonstration | UAT, demo script, documentation, handover |

# Week 1  17 to 23 August

Focus. Foundation and Classification Completeness Agent

Planned work.

Confirm motor-claim document scope, required-document matrix, claim lifecycle, and the single Claims Adjuster human-review policy.

Set up the FastAPI project structure, configuration, test suite, local run instructions, CORS, and environment templates.

Implement document intake, supported file checks, duplicate detection, readability checks, content-based document classification, wrong-document detection, and completeness results.

Create synthetic PDFs and images for claim form, RC, policy, driving licence, FIR, estimate, invoice, and accident photos.

Expose standalone classification and completeness APIs for the frontend.

Week exit criteria. A package can be uploaded locally; valid, missing, duplicate, unreadable, ambiguous, and wrong-document outcomes are visible in API responses.

# Week 2  24 to 30 August

Focus. Extraction and Cross Document Validation Agent

Planned work.

Add deterministic extraction for identifiers, dates, vehicle data, policy dates, garage values, and licence fields.

Use Azure OpenAI only to enrich or verify extraction when deterministic extraction is incomplete; preserve the extraction method in output.

Implement field validation and cross-document comparisons for vehicle registration, claimant, accident date, policy period, garage totals, and licence validity.

Build the LangGraph workflow through validation, triage, and the Claims Adjuster review boundary.

Add tests for consistent and inconsistent claim packages.

Week exit criteria. A full claim package produces structured extraction output, field issues, cross-document issues, routing reason, and an auditable workflow result.

# Week 3  31 August to 6 September

Focus. Fraud Coverage Assessment and Settlement Agents

Planned work.

Implement transparent fraud indicators: duplicate files, repeated identifiers, cross-document conflicts, estimate-to-invoice variance, and LLM-generated review hypotheses.

Add policy retrieval from approved policy wording and deterministic coverage checks for active policy period, licence validity, IDV, limits, exclusions, and deductibles where data is available.

Generate a claims assessment brief, reviewer checklist, and preliminary settlement recommendation. These remain recommendations, never automated approval or rejection.

Consolidate all automated evidence into one durable Claims Adjuster review task.

Week exit criteria. Every completed package has fraud, coverage, assessment, settlement, and review-task evidence. Decisions remain human controlled.

# Week 4  7 to 13 September

Focus. Azure Integration UI Integration and Operational Readiness

Planned work.

Configure Azure Blob Storage for source documents, Azure PostgreSQL for metadata and review tasks, Azure Document Intelligence for scanned-document OCR, and Azure OpenAI for controlled reasoning.

Connect the UI upload, triage, policy enquiry, Claims Adjuster review-task retrieval, and decision submission flows to the backend APIs.

Add LangSmith or Langfuse tracing configuration, structured logs, audit events, error handling, and environment-specific configuration guidance.

Run happy-path and exception-path end-to-end tests with Azure services enabled.

Week exit criteria. A real uploaded claim is stored, processed, persisted, visible to the Claims Adjuster, and resolved through one recorded human decision.

# Closeout Window  14 to 17 September

| Date | Activity | Output |
| --- | --- | --- |
| 14 Sep | Integration regression and data reset | Repeatable demo environment and resolved critical defects |
| 15 Sep | User acceptance walkthrough | Feedback log and accepted demo scenarios |
| 16 Sep | Demo rehearsal and documentation review | Final demo script, architecture explanation, codebase guide |
| 17 Sep | Cohort demonstration and handover | Live demonstration, known limitations, next-phase backlog |

# Roles and Decision Rights

| Role | Primary responsibility | Decision right |
| --- | --- | --- |
| Product and claims lead | Scope, claim rules, policy interpretation, UAT | Accepts business outcomes and prioritises backlog |
| Backend and AI team | Agents, APIs, LangGraph, Azure integrations, tests | Implements technical design and safety controls |
| Frontend team | Claimant and Claims Adjuster UI workflows | Validates API integration and usability |
| Claims Adjuster | Reviews evidence, approves, rejects, or requests more information | Only role permitted to make claim decisions |
| Platform and security | Azure access, networking, Key Vault, monitoring | Approves production configuration and access controls |

# Key Risks and Controls

| Risk | Control | Owner |
| --- | --- | --- |
| Scanned PDFs are unreadable | Enable Document Intelligence prebuilt-read; route low-confidence OCR to the Claims Adjuster. | Backend and AI |
| LLM produces unsupported interpretation | Ground prompts in extracted fields and approved clauses; keep deterministic rules and human decision authority. | Backend and claims |
| Azure service setup delays | Use local deterministic test fixtures first; complete Azure credentials and firewall setup during Week 4. | Platform |
| Demo uses inconsistent data | Maintain a small approved synthetic data pack with expected outcomes and reset instructions. | Team |
| Secrets appear in code or logs | Use `.env` only locally; move secrets to Key Vault and use Managed Identity for production. | Platform and security |

# Final Demonstration Checklist

Azure Blob upload works and source documents are visible in the configured container.

PostgreSQL records claim metadata, document results, review tasks, and audit events.

Azure OpenAI and Document Intelligence are configured without exposing keys to the UI.

One sample package passes through all agents and produces clear evidence for the Claims Adjuster.

One inconsistent or suspicious package is correctly routed for human review rather than auto-decided.

Claims Adjuster decision is persisted and the final status is visible in the UI.

Demo team can explain deterministic controls, LLM usage, auditability, and known limitations.

# Daily Delivery Cadence

| Cadence | Practice | Evidence |
| --- | --- | --- |
| Daily | 15 minute delivery check covering completed work, blockers, Azure access needs, and the next test case. | Updated task board and blocker owner |
| Twice weekly | Claims and engineering review of extraction quality, routing decisions, and policy-rule assumptions. | Reviewed sample outputs and rule changes |
| Weekly | Demonstrate the week objective against the exit criteria and agree the next-week scope. | Accepted milestone or recorded recovery plan |
| Before demo | Run a clean synthetic claim package and one exception scenario from a documented script. | Repeatable demo evidence and known-limitations list |